## Final Timeline
SIT253 – Echoes of the Forest ¦ Final Folio Timeline
Task | Start Week | End Week | Status | Progress | W13 | W14 | W15 | W16
Review Progressive Folio 2 feedback | W13 | W13 | Completed | 100% | ■
Finalise 3D visual assets | W13 | W14 | Completed | 100% | ■ | ■
Finalise textures & materials | W13 | W14 | Completed | 100% | ■ | ■
Organise asset management | W14 | W14 | In Progress | 70% |  | ■
Capture asset management evidence | W14 | W14 | In Progress | 70% |  | ■
Record / finalise original audio assets | W13 | W14 | In Progress | 70% | ■ | ■
Edit and document audio assets | W14 | W14 | In Progress | 70% |  | ■
Finalise lighting & composition | W14 | W14 | Planned | 90% |  | ■
Produce final asset renders | W14 | W15 | Planned | 90% |  | ■ | ■
Produce final environment renders | W14 | W15 | Planned | 90% |  | ■ | ■
Update concept & development documentation | W14 | W15 | Planned | 90% |  | ■ | ■
Finalise website / online folio | W15 | W16 | Planned | 90% |  |  | ■ | ■
Add development comparison | W15 | W15 | Planned | 90% |  |  | ■
Complete final reflection | W15 | W15 | Planned | 90% |  |  | ■
Complete ethics & GenAI documentation | W15 | W15 | Planned | 90% |  |  | ■
Finalise references | W15 | W15 | Planned | 90% |  |  | ■
Final folio review & corrections | W16 | W16 | Planned | 90% |  |  |  | ■
Create frozen folio PDF | W16 | W16 | Planned | 90% |  |  |  | ■
Final submission | W16 | W16 | Planned | 90% |  |  |  | ■
Status Legend
Completed
In Progress
Planned

## Gantt View
Final Folio – Gantt Overview
Task | Progress | W13 | W14 | W15 | W16
Review Progressive Folio 2 feedback | 100% | ■
Finalise 3D visual assets | 100% | ■ | ■
Finalise textures & materials | 100% | ■ | ■
Organise asset management | 70% |  | ■
Capture asset management evidence | 70% |  | ■
Record / finalise original audio assets | 70% | ■ | ■
Edit and document audio assets | 70% |  | ■
Finalise lighting & composition | 90% |  | ■
Produce final asset renders | 90% |  | ■ | ■
Produce final environment renders | 90% |  | ■ | ■
Update concept & development documentation | 90% |  | ■ | ■
Finalise website / online folio | 90% |  |  | ■ | ■
Add development comparison | 90% |  |  | ■
Complete final reflection | 90% |  |  | ■
Complete ethics & GenAI documentation | 90% |  |  | ■
Finalise references | 90% |  |  | ■
Final folio review & corrections | 90% |  |  |  | ■
Create frozen folio PDF | 90% |  |  |  | ■
Final submission | 90% |  |  |  | ■